## Sheet1
| ENGINEERING CHANGE ORDER | POSCON - TOP LEVEL
Release ID | Change | Who | Assembly | Reason | Date
POSCON.v1.0 | None | Rafael Send | n/a | First production version of new POSCON | 2014-10-13
POSCON.v1.1 | Fixed backplate stud size | Marc Levinson | .MECH | Inconsistent labeling between drawing and BOM | 2014-10-15
| Moved PCB production files out, back into respective repos | Rafael Send | .PCB | Top level should not contain production files | 2014-10-15
| Updated top level BOM to reflect new component tags | Rafael Send | TOP | Consistent naming | 2014-10-15
POSCON.v1.2 | Changes to POSCON.FACE & POSCON.BACK, added new part POSCON.CORE. New mounting schema. (Snaps) | Ethan Dale | .MECH | NewPOSCON.CORE part, redesign POSCON.BACK & POSCON.FACE, delete superseded parts | 2015-05-08
| POSCON.PCB.v1.3 with LED and silkscreen fix. [v1.2 from Jan 13th never released at the top level: 5V MCU, 7Seg resistor, power trace and tented via upgrades] | Rafael Send | .PCB | Putwall LED (v1.3) & higher voltage (v1.2) compatible | 2015-08-11
POSCON.v1.3 | Added 0.031” radius to notches on back of POSCON.FACE | Ethan Dale | .MECH | First articles came back from vendor with radiused notches, drawing change made to reduce future potential for confusion | 2015-09-09
| Corrected date on drawing to 09/09/2015 | Ethan Dale | .MECH | Good data hygiene | 2015-09-10
| Included packing and assembly docs in BOM | Calla Belkin | TOP | Incomplete documentation | 2015-10-07